## Launch Checklist
Tally Connect — Launch Checklist
Updated: March 26, 2026
# | Task | Category | Priority | Owner | Status | Est. Hours | Dependencies | Notes
CRITICAL BLOCKERS
1 | Verify CI passes on latest main push | Critical | P0 | Dev | Not Started | 1 | - | CI failed on 1b5f956 and 398a795
2 | Redeploy relay-server to Railway | Critical | P0 | Dev | Not Started | 1 | CI green | Build failed Mar 21 — production may be stale
3 | Fix landing page signup plan selection | Critical | P0 | Dev | Not Started | 3 | - | Everyone lands on Connect regardless of CTA
4 | Add prices to billing page in portal | Critical | P0 | Dev | Not Started | 4 | - | Users can't see what they're paying for
5 | End-to-end signup → trial → upgrade test | Critical | P0 | Dev | Not Started | 4 | Items 1-4 | Full Stripe flow on staging
6 | Verify auto-update works with real GitHub Release | Critical | P0 | Dev | Not Started | 3 | CI green | Create test release, verify download + install
7 | Apple Developer certificate + notarization | Critical | P0 | Dev | Not Started | 4 | - | macOS Gatekeeper blocks unsigned apps
PRE-LAUNCH
8 | Per-user portal login accounts | Pre-Launch | P1 | Dev | Not Started | 16 | - | Currently 1 shared login per church
9 | Email notification fallback for alerts | Pre-Launch | P1 | Dev | Not Started | 12 | - | Telegram is only channel — single point of failure
10 | Billing page: show tier prices + feature comparison | Pre-Launch | P1 | Dev | Not Started | 6 | Item 4 | Users need to understand what they're upgrading to
11 | Portal code splitting / lazy loading | Pre-Launch | P1 | Dev | Not Started | 8 | - | 590KB single-file SPA — slow on mobile
12 | Forgot password link in Electron app | Pre-Launch | P1 | Dev | Not Started | 2 | - | No in-app path to password recovery
13 | Complete Spanish i18n coverage | Pre-Launch | P1 | Dev | Not Started | 8 | - | Login page, billing modals, server errors still English
14 | Landing page SEO meta tags audit | Pre-Launch | P1 | Marketing | Not Started | 3 | - | OG image 404, missing structured data
15 | Create product demo video (2-3 min) | Pre-Launch | P1 | Marketing | Not Started | 12 | - | Show setup → monitoring → alert flow
16 | Write 3 launch blog posts | Pre-Launch | P1 | Marketing | Not Started | 8 | - | Intro, use case story, comparison
17 | Set up Google Analytics + conversion tracking | Pre-Launch | P1 | Marketing | Not Started | 3 | - | Track signup funnel
18 | Privacy policy + Terms of Service pages | Pre-Launch | P1 | Ops | Not Started | 6 | - | Required before collecting payments
19 | Support email + helpdesk setup | Pre-Launch | P1 | Ops | Not Started | 3 | - | support@tallyconnect.app
20 | Redis/Upstash for production rate limiting | Pre-Launch | P1 | Dev | Not Started | 4 | - | In-memory rate limiter won't scale
21 | Stripe webhook endpoint SSL verification | Pre-Launch | P2 | Dev | Not Started | 2 | - | Confirm webhook signatures in production
22 | Onboarding email sequence (5 emails) | Pre-Launch | P2 | Marketing | Not Started | 8 | - | Welcome → Setup → First service → Value → Upgrade
23 | ROI Calculator wired to landing page | Pre-Launch | P2 | Dev | Not Started | 2 | - | Component built but never rendered
24 | Knowledge base / FAQ docs | Pre-Launch | P2 | Marketing | Not Started | 10 | - | Setup guides, troubleshooting, billing FAQ
LAUNCH DAY
25 | Publish v1.1.0 GitHub Release (signed DMG + EXE) | Launch | P0 | Dev | Not Started | 2 | Items 6,7 | Triggers auto-update for any beta users
26 | Deploy relay-server to Railway production | Launch | P0 | Dev | Not Started | 1 | All pre-launch done | Final production deploy
27 | Publish landing page updates to Vercel | Launch | P0 | Dev | Not Started | 1 | - | Final copy, pricing, CTA fixes
28 | Send launch announcement email | Launch | P0 | Marketing | Not Started | 2 | - | To beta users + waitlist
29 | Post on church AV Facebook groups | Launch | P1 | Marketing | Not Started | 2 | - | Church Tech Leaders, AVL, etc.
30 | Post on Reddit r/churchav r/livesound | Launch | P1 | Marketing | Not Started | 1 | - | Authentic intro, not spammy
31 | Monitor error logs + Stripe dashboard | Launch | P0 | Dev | Not Started | 4 | - | All day — watch for signup failures
POST-LAUNCH (Weeks 1-4)
32 | Daily error log review + hotfix cycle | Post-Launch | P0 | Dev | Not Started | 2 | - | Per day — first 2 weeks
33 | Collect NPS from first 10 churches | Post-Launch | P1 | Marketing | Not Started | 3 | - | Simple survey after 1 week
34 | Fix top 3 user-reported issues | Post-Launch | P1 | Dev | Not Started | 12 | - | Budget 4 hrs each
35 | Church spotlight / case study | Post-Launch | P2 | Marketing | Not Started | 6 | - | Interview a happy beta church
36 | Planning Center integration docs | Post-Launch | P2 | Dev | Not Started | 4 | - | Self-serve setup guide
37 | PWA manifest for mobile portal | Post-Launch | P2 | Dev | Not Started | 4 | - | Add to Home Screen support
38 | Cross-campus unified dashboard | Post-Launch | P2 | Dev | Not Started | 16 | - | Multi-campus admin single view
39 | Referral program setup | Post-Launch | P3 | Marketing | Not Started | 6 | - | Churches referring churches
40 | Monthly product update email | Post-Launch | P3 | Marketing | Not Started | 3 | - | Changelog + tips newsletter
41 | App Store / Homebrew distribution | Post-Launch | P3 | Dev | Not Started | 8 | - | Easier discovery and install
[5 empty] | TOTAL HOURS: | 210

## Timeline
Tally Connect — Launch Timeline
Target Launch: Week of May 25, 2026 (~9 weeks)
Week | Dates | Phase | Dev Tasks (~20 hrs) | Marketing/Ops Tasks (~10 hrs) | Milestone
Week 1 | Mar 30 – Apr 5 | Fix Blockers | CI fixes, Railway redeploy, signup plan selection fix, billing page prices | Set up analytics, start demo video script | CI green, production live
Week 2 | Apr 6 – 12 | Fix Blockers | E2E signup→trial→upgrade test, auto-update verification, Apple cert submission | Draft launch blog post #1, SEO audit fixes | Stripe flow verified end-to-end
Week 3 | Apr 13 – 19 | Core Polish | Per-user portal accounts (part 1), forgot password link, Redis rate limiting | Privacy policy + ToS drafts, support email setup | Portal auth redesign started
Week 4 | Apr 20 – 26 | Core Polish | Per-user portal accounts (part 2), email notification fallback | Onboarding email sequence (5 emails), knowledge base start | Multi-user portal live
Week 5 | Apr 27 – May 3 | Launch Prep | Portal code splitting, Spanish i18n completion, ROI calculator wiring | Demo video production, blog posts #2 and #3 | Portal under 200KB initial load
Week 6 | May 4 – 10 | Beta Outreach | Bug fixes from beta feedback, webhook SSL verification | Reach out to 10 churches for beta, FAQ docs | 5 beta churches actively using
Week 7 | May 11 – 17 | Beta Outreach | Top beta bug fixes, Stripe edge cases | Collect beta feedback, refine messaging, prep launch email | 10 beta churches, feedback collected
Week 8 | May 18 – 24 | Final Prep | Final QA pass, staging → production, notarized build | Launch email drafted, social posts queued | Launch-ready build signed & tested
Week 9 | May 25 – 31 | LAUNCH | Publish release, deploy production, monitor logs all week | Launch email, Facebook groups, Reddit, Product Hunt? | 🚀 LIVE — first paid signups
Week 10 | Jun 1 – 7 | Post-Launch | Daily hotfix cycle, top 3 reported issues | NPS survey to early users, monitor conversion funnel | First MRR milestone
Week 11 | Jun 8 – 14 | Post-Launch | Planning Center integration docs, PWA manifest | Church spotlight / case study interview | Case study published
Week 12 | Jun 15 – 21 | Post-Launch | Cross-campus dashboard (part 1) | Referral program setup, monthly newsletter | Multi-campus feature preview
Week 13 | Jun 22 – 28 | Post-Launch | Cross-campus dashboard (part 2), App Store prep | Product update email, analyze churn | 30-day post-launch review

## Goals & Metrics
Tally Connect — Goals & Metrics
Metric | Target | Stretch Goal | How to Measure | Notes
PRE-LAUNCH (Weeks 1-8)
Beta churches onboarded | 10 | 15 | Stripe customer count (trial) | Personal outreach to local churches + online communities
Open bugs (P0/P1) | 0 | 0 | GitHub Issues | Zero P0/P1 at launch gate
CI pass rate | 100% | 100% | GitHub Actions | All 3 test suites green
Lighthouse score (landing page) | 90+ | 95+ | PageSpeed Insights | Performance, SEO, Accessibility
Beta NPS score | 40+ | 60+ | Survey (1-10 scale) | Anything above 30 is good for beta
LAUNCH WEEK (Week 9)
New signups | 25 | 50 | Stripe + DB | Free + paid combined
Paid conversions (trial → Plus/Pro) | 3 | 8 | Stripe dashboard | ~12% conversion rate target
Landing page → signup conversion | 5% | 8% | Google Analytics funnel | Industry avg is 2-5% for SaaS
Uptime | 99.9% | 100% | Health endpoint monitor | No downtime during launch week
Support tickets | <10 | <5 | Email inbox | Low = good onboarding
30-DAY (Week 13)
Total churches (free + paid) | 40 | 75 | DB count | Includes free Connect tier
Paying churches | 8 | 15 | Stripe active subscriptions | Plus, Pro, or Enterprise
MRR | $350 | $700 | Stripe MRR dashboard | 8 × avg $44/mo
Monthly churn rate | <5% | <3% | Stripe cancellations / active | First-month churn is typically higher
NPS score | 50+ | 65+ | Survey | Good = 50+, Great = 70+
90-DAY (Month 3)
Total churches | 80 | 150 | DB count | Organic + referral growth
Paying churches | 20 | 40 | Stripe | 25% paid conversion rate
MRR | $1,200 | $2,500 | Stripe | Blended avg ~$60/mo
Annual run rate | $14,400 | $30,000 | MRR × 12 | ARR milestone
Referral signups | 5 | 15 | Referral tracking | Churches referring churches
Feature requests logged | 20 | 30 | GitHub Issues / feedback | Signal of engagement

## Revenue Projections
Tally Connect — Revenue Projections (6-Month)
Pricing Table
Tier | Monthly Price
Connect | 0
Plus | 29
Pro | 79
Enterprise | 199
Conservative Scenario
| Subscribers | Month 1 Jun '26 | Month 2 Jul '26 | Month 3 Aug '26 | Month 4 Sep '26 | Month 5 Oct '26 | Month 6 Nov '26
Connect | Count | 5 | 10 | 15 | 20 | 25 | 30
Plus | Count | 1 | 2 | 4 | 6 | 8 | 10
Pro | Count | 0 | 1 | 1 | 2 | 3 | 4
Enterprise | Count | 0 | 0 | 0 | 0 | 0 | 1
| MRR | 29 | 137 | 195 | 332 | 469 | 805
| Total Subs | 6 | 13 | 20 | 28 | 36 | 45
Moderate Scenario
| Subscribers | Month 1 Jun '26 | Month 2 Jul '26 | Month 3 Aug '26 | Month 4 Sep '26 | Month 5 Oct '26 | Month 6 Nov '26
Connect | Count | 8 | 18 | 30 | 40 | 50 | 60
Plus | Count | 2 | 5 | 8 | 12 | 16 | 20
Pro | Count | 1 | 2 | 4 | 6 | 8 | 10
Enterprise | Count | 0 | 0 | 1 | 1 | 2 | 2
| MRR | 137 | 303 | 747 | 1021 | 1494 | 1768
| Total Subs | 11 | 25 | 43 | 59 | 76 | 92
Optimistic Scenario
| Subscribers | Month 1 Jun '26 | Month 2 Jul '26 | Month 3 Aug '26 | Month 4 Sep '26 | Month 5 Oct '26 | Month 6 Nov '26
Connect | Count | 15 | 30 | 50 | 70 | 90 | 110
Plus | Count | 3 | 8 | 15 | 22 | 30 | 38
Pro | Count | 2 | 4 | 8 | 12 | 16 | 20
Enterprise | Count | 0 | 1 | 2 | 3 | 4 | 5
| MRR | 245 | 747 | 1465 | 2183 | 2930 | 3677
| Total Subs | 20 | 43 | 75 | 107 | 140 | 173
Scenario Comparison — Month 6 MRR
Scenario | Month 6 MRR | Month 6 ARR | Month 6 Paid Subs
Conservative | 805 | 9660 | 15
Moderate | 1768 | 21216 | 32
Optimistic | 3677 | 44124 | 63